## Detailed Info
SUMMARY
Sr. No. | Description | Remark
1 | Name Of Project | CONSTRUCTION OF PROPOSED SUB MARKET AT KHEDSHIVAPUR, DIST. PUNE FOR KRUSHI UTPANNA BAZAR SAMITI SHREE CHATRAPATI SHIVAJI MARKET YARD, PUNE
2 | Name of Client | Krushi Utpanna Bazar Samitee, Market Yard, Pune- 411037
3 | Name of Contractor | M/s UNIVASTU INDIA LTD
4 | Cost Of Tender | Rs. 24,73,80,891/- + GST
5 | Completion Period | 24 Months
6 | Tender Submission Last Date | 31/08/2019
7 | Work Order No. | जा. क्र. प्रजा/स्थापत्य/उ. बा. खेडशीवापूर/आठ. बाजार/वर्क ऑर्डर/ २०७७/२०१९-२० दि. १९/०९/२०१९
8 | Work Order Date | 19/09/2019
9 | Our Final Quoted Amount | Rs. 23,04,95,000/- (6.83 % Below) + GST | 247280891
10 |  |  | 230495000
16785891
6.788%

## Summary
SUMMARY OF ESCALATION BILL
Sr. No. | Description | Amount As per Escalation Rs. | Amount As per Escalation Rs. Crore | % wrt Total Amount
1 | Labour | 16473715.6562 | 1.6474 | 28.06%
2 | Material Component | 37875836.053 | 3.7876 | 64.52%
3 | P.O.L | 1209443.5392 | 0.12094 | 2.06%
4 | TMT Steel | 2600901.7086 | 0.26009 | 4.43%
5 | Cement | 544955.1563 | 0.054496 | 0.9283%
A | Total Amount | 58704852.1133 | 5.8705 | 100% | 25.47% | 4.245%
B | CGST 9% | 5283436.6902
C | SGST 9% | 5283436.6902
D | Total After GST | 69271726

## Labour
STATEMENT SHOWING CALCULATION OF PRICE ESCALATION | [5 empty] | LABOUR
Percentage of Components as per agrement |  | BASIC INDICES |  |  | STAR RATE OF CEMENT |  | 4700 Rs per MT |  | STAR RATE OF STEEL |  | 45785 Rs per MT
1 LABOUR | 22% | 1. LABOUR | 316.3333 | Agreement No
2 MATERIAL | 76% | 2. MATERIAL |  | Name of Agency |  | : M/s UNIVASTU INDIA LTD
3 P.O.L. | 2% | 3. P.O.L. |  | Name of Work |  | Construction of sub market at khedshivapur
|  | 4. CEMENT | [10 empty] | 0.22
|  | 5. STEEL |  | Date of Receipt |  | : 31.08.2019
[9 empty] | 2011-08-01 | 202 | 204
[9 empty] | 2011-09-01 | 204
[9 empty] | 2011-10-01 | 206
612
Period of work done considered for price Escalation | R. A. Bill No. | Construction of work done (B) during the period (As per column No 1 After deducting the amount of Extra items | Cost of Schedule A (Cement & Steel) Material consumed for the work done during the period | P = ( 3- 4 ) | Month | Monthly Indices for Labour | Quarterly average Index Labour | VL = (P x 0.85) | = P (-) Cost of Schedule "A" Material used | K1/100 | = VL x(K1/100)x(L1-L0)/L0 | 275
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2025-10-31 | R A Bill No 01 | 230495000 | 19375880.5521 | 211119119.4479 | 2025-08-01 | 444.682 | 448.3313 | 179451251.5307 |  | 0.22 | 16473715.6562 | 2019-05-01 | 314 | 316.3333
[5 empty] | 2025-09-01 | 444.682 | [5 empty] | 2019-06-01 | 316
[5 empty] | 2025-10-01 | 455.63 | [5 empty] | 2019-07-01 | 319
[6 empty] | 1344.994 | [6 empty] | 949
|  | 230495000 | 19375880.5521 | 211119119.4479 |  |  |  | 179451251.5307 |  |  | 16473715.6562
230495000
| 19375880.5521 | [10 empty] | 2014-10-01 | 1220.16 | 1220.16
| 211119119.4479 | [10 empty] | 2014-11-01 | 1220.16
[12 empty] | 2014-12-01 | 1220.16
165101326.2572

## Other material
STATEMENT SHOWING CALCULATION OF PRICE ESCALATION | [5 empty] | OTHER MATERIAL
Percentage of Components as per agrement |  | BASIC INDICES |  |  | STAR RATE OF CEMENT |  | 4700 Rs per MT |  | STAR RATE OF STEEL |  | 45785 Rs per MT
1 LABOUR | 22% | 1. LABOUR |  | Agreement No
2 MATERIAL | 76% | 2. MATERIAL | 121.4667 | Name of Agency |  | : M/s UNIVASTU INDIA LTD
3 P.O.L. | 2% | 3. P.O.L. |  | Name of Work |  | Construction of sub market at khedshivapur
4. CEMENT
|  | 5. STEEL |  | Date of Receipt |  | : 31.08.2019
[9 empty] | 2011-10-01 | 157 | 0
[9 empty] | 2011-11-01 | 157.4
[9 empty] | 2011-12-01 | 157.3
Period of work done considered for price Escalation | R. A. Bill No. | Construction of work done (B) during the period (As per column No 1 After deducting the amount of Extra items | Cost of Schedule A (Cement & Steel) Material consumed for the work done during the period | P = ( 3- 4 ) | Month | Monthly Indices for Other material | Quarterly average Index Other material | VL = (P x 0.85) | = P (-) Cost of Schedule "A" Material used | K2/100 | =VL x (K2/100) x(M1-M0)/M0
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2025-10-31 | R A Bill No 01 | 230495000 | 19375880.5521 | 211119119.4479 | 2025-08-01 | 155.2 | 155.2 | 179451251.5307 |  | 0.76 | 37875836.053 | 2019-05-01 | 121.6 | 121.4667
[5 empty] | 2025-09-01 | 155.2 | [5 empty] | 2019-06-01 | 121.5
[5 empty] | 2025-10-01 | 155.2 | [5 empty] | 2019-07-01 | 121.3
[6 empty] | 465.6 | [6 empty] | 364.4
|  | 230495000 | 19375880.5521 | 211119119.4479 |  |  |  | 179451251.5307 |  |  | 37875836.053

## P.O.L
STATEMENT SHOWING CALCULATION OF PRICE ESCALATION | [5 empty] | P. O. L.
Percentage of Components as per agrement |  | BASIC INDICES |  |  | STAR RATE OF CEMENT |  | 4700 Rs per MT |  | STAR RATE OF STEEL |  | 45785 Rs per MT
1 LABOUR | 22% | 1. LABOUR |  | Agreement No
2 MATERIAL | 76% | 2. MATERIAL |  | Name of Agency |  | : M/s UNIVASTU INDIA LTD
3 P.O.L. | 2% | 3. P.O.L. | 67.57 | Name of Work |  | Construction of sub market at khedshivapur
4. CEMENT
|  | 5. STEEL |  | Date of Receipt |  | : 31.08.2019
Period of work done considered for price Escalation | R. A. Bill No. | Construction of work done (B) during the period (As per column No 1 After deducting the amount of Extra items | Cost of Schedule A (Cement & Steel) Material consumed for the work done during the period | P = ( 3- 4 ) | Month | Monthly Indices for P.O.L | Quarterly average Index P.O.L | VL = (P x 0.85) | = P (-) Cost of Schedule "A" Material used | K3/100 | =VL x(K1/100)x(P1-P0)/P0
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2025-10-31 | R A Bill No 01 | 230495000 | 19375880.5521 | 211119119.4479 | 2025-08-01 | 90.34 | 90.34 | 179451251.5307 |  | 2% | 1209443.5392 | 2019-05-01 | 68.52 | 67.57
[5 empty] | 2025-09-01 | 90.34 | [5 empty] | 2019-06-01 | 67.155
[5 empty] | 2025-10-01 | 90.34 | [5 empty] | 2019-07-01 | 67.035
[6 empty] | 271.02 | [6 empty] | 202.71
|  | 230495000 | 19375880.5521 | 211119119.4479 |  |  |  | 179451251.5307 |  |  | 1209443.5392

## TMT
STATEMENT SHOWING CALCULATION OF PRICE ESCALATION | [5 empty] | STEEL
Percentage of Components as per agrement |  | BASIC INDICES |  |  | STAR RATE OF CEMENT |  | 4700 Rs per MT |  | STAR RATE OF STEEL |  | 45785 Rs per MT
1 LABOUR | 11% | 1. LABOUR |  | Agreement No
2 MATERIAL | 76% | 2. MATERIAL |  | Name of Agency |  | : M/s UNIVASTU INDIA LTD
3 P.O.L. | 13% | 3. P.O.L. |  | Name of Work |  | Construction of sub market at khedshivapur
4. CEMENT
|  | 5. STEEL | 107.9667 | Date of Receipt |  | : 31.08.2019
Period of work done considered for price Escalation | R. A. Bill No. | Construction of work done (B) during the period (As per column No 1 After deducting the amount of Extra items | Cost of Schedule A (Cement & Steel) Material consumed for the work done during the period | P = ( 3- 4 ) | Month | Monthly Indices for Steel | Quarterly average Index Steel | VL = (P x 0.85) | = P (-) Cost of Schedule "A" Material used |  | S0 (SI1-SI0) x T SI0
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2025-10-31 | R A Bill No 01 |  |  |  | 2025-08-01 | 135.2 | 135.0667 |  |  |  | 2600901.7086 | 2019-05-01 | 109.4 | 107.9667
[5 empty] | 2025-09-01 | 135.6 | [5 empty] | 2019-06-01 | 108.4
[5 empty] | 2025-10-01 | 134.4 | [5 empty] | 2019-07-01 | 106.1
[6 empty] | 405.2 | [6 empty] | 323.9
2600901.7086

## Cement
STATEMENT SHOWING CALCULATION OF PRICE ESCALATION | [5 empty] | CEMENT
Percentage of Components as per agrement |  | BASIC INDICES |  |  | STAR RATE OF CEMENT |  | 4700 Rs per MT |  | STAR RATE OF STEEL |  | 45785 Rs per MT
1 LABOUR | 11% | 1. LABOUR |  | Agreement No
2 MATERIAL | 76% | 2. MATERIAL |  | Name of Agency |  | : M/s UNIVASTU INDIA LTD
3 P.O.L. | 13% | 3. P.O.L. |  | Name of Work |  | Construction of sub market at khedshivapur
|  | 4. CEMENT | 122.1
|  | 5. STEEL |  | Date of Receipt |  | : 31.08.2019
Period of work done considered for price Escalation | R. A. Bill No. | Construction of work done (B) during the period (As per column No 1 After deducting the amount of Extra items | Cost of Schedule A (Cement & Steel) Material consumed for the work done during the period | P = ( 3- 4 ) | Month | Monthly Indices for Cement | Quarterly average Index Cement | VL = (P x 0.85) | = P (-) Cost of Schedule "A" Material used |  | C0 (CI1-CI0) x T CI0
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2025-10-31 | R A Bill No 01 |  |  |  | 2025-08-01 | 130.7 | 129.7333 |  |  |  | 544955.1563 | 2019-05-01 | 123.2 | 122.1
[5 empty] | 2025-09-01 | 130 | [5 empty] | 2019-06-01 | 122.5
[5 empty] | 2025-10-01 | 128.5 | [5 empty] | 2019-07-01 | 120.6
[6 empty] | 389.2 |  |  |  |  | 544955.1563 |  | 366.3

## Material details
Agreement No
Name of Agency |  | : M/s UNIVASTU INDIA LTD
Name of Work
DETAILS OF MATERIAL CONSUMED IN THIS BILL
Month | Bill No. | Material | Quantity | Unit | Rate | Amount
2025-10-31 | R.A.Bill no.01 | Cement | 1584.8914 | M.T | 4700 | 7448989.6521 | 5800 | 1100 | 1743380.5569
|  | TMT | 226.74 | M.T | 45785 | 10381290.9 | 49000 | 3215 | 728969.1
|  | Structural Steel | 33.6 | M.T | 46000 | 1545600
|  |  |  | Total R.A.Bill No.01 |  | 19375880.5521
|  |  |  | Grand Total |  | 19375880.5521

## CEMENT-1 (hidden)
CEMENT CONSUMPTION STATEMENT
Name of Work:- Construction of Inftrastructure Project for National Institute of Post Harvest Technology at Talegaon Dabhade Dist Pune |  |  |  |  | Agreement No.:- B-1/CE/1 for 2011-2012
Name of Contractor:- Prakash Constroweel Limited Nasik. Tal & Dist Nasik. |  |  |  |  | Bill No.- Ist R.A.Bill
Item No. | Item of work in brief. | Executed Quantity | Therotical rate of consumption of Bitumen/Cement | Unit | Bitumen in M.T./ Cement in Bags | Remarks.
Required as per theoretical calculations.
16 |  |  | 4.05 | Cum | 0 | M.B.No P.No
17 |  |  | 3.2 | Cum | 0
18 |  |  | 6.8 | Cum | 0
19 |  |  | 6.8 | Cum | 0
20 |  |  | 6.8 | Cum | 0
32 |  |  | 1.44 | Cum | 0
|  |  |  | Total | 0 | 0
M.T.

## Cement-Con-1 (hidden)
CEMENT CONSUMPTION STATEMENT
Sr.no. | Description | R.A. Bill No. 1 | R.A. Bill No. 2 | R.A. Bill No. 3 | R.A. Bill No. 4 | R.A. Bill No. 5 | R.A. Bill No. 6 | R.A. Bill No. 7 | R.A. Bill No. 8 | R.A. Bill No. 9 | R.A. Bill No. 10 | R.A. Bill No. 11 | R.A. Bill No. 12 | Total Quantity
16 | P & L in situ c.c 1:3:6 | 23.364 | 31.8 | 182.6415 | 33.042 | 12.3795 |  |  | 2.607 |  |  |  |  | 285.834
17 | P & L in situ c.c 1:4:8 | 4.4698 |  | 12.4745 | 0 | 70.2551 |  |  | 67.4003 | 22.0583 |  |  | 45.57 | 222.228
18 | P & L M-20 for Footing | 46.185 | 67.9605 | 61.02 | 56.7905 | 29.221 |  |  | 6.024 |  |  |  |  | 267.201
19 | P & L M-20 for Column | 8.8205 | 11.0848 | 74.99 | 85.457 | 29.75 | 2 | 23.2565 | 48.0852 | 44.45 | 4.7817 | 22.2277 | 3.91 | 358.8133
20 | P & L M-20 for Beam | 19.438 | 29.3554 | 120.29 | 48.2118 | 100.31 | 58.33 | 2.62 | 73.26 | 70.94 | 129.81 |  | 30.83 | 683.3951
21 | P & L M-20 for Slab |  | 30.703 | 32.11 | 43.3966 | 50.09 | 80.38 | 133.85 | 83.82 | 77.88 | 130.925 |  | 5.2 | 668.3546
22 | P & L M-20 for Lintel |  |  | 4.41 | 4.56 | 8.37 | 4.08 | 15.82 | 2.537 | 4.99 | 12.9182 |  |  | 57.6852
23 | P & L M-20 for Steps | [9 empty] | 5.985 |  |  | 5.985
24 | P & L M-20 for Paradi |  |  |  |  | 1.54 |  |  |  |  | 8.2446 |  |  | 9.7846
25 | P & L M-20 for coping | [12 empty] | 0
26 | P & L M-20 for Chajja |  |  |  |  | 4.82 |  | 2.4 | [5 empty] | 7.22
32 | BBM in CM 1:6 | 13.4095 |  | 77.75 | 145.3 | 39.93 | 195.18 | 218.8671 | 175.19 | 166.73 | 544.47 | 216.0601 | 229.27 | 2022.1566
| BBM in CM 1:4 | [5 empty] | 24.27 |  | 36.45 | 24.3 | 48.6 |  |  | 133.62
38 | Plaster 20 mm |  |  |  |  | 914.47 | 1260.11 | 1267.1565 | 630.3692 | 1198.14 | 5818.08 |  | 14.61 | 11102.9357
36 | Ceiling Plaster |  |  |  | 176.28 |  | 402.22 |  | 221.3175 | 386.74 | 1157.92 |  | 20.03 | 2364.5075
40 | Sand Faced Plaster | [7 empty] | 1119.26 | 1040.02 | 1947.44 |  | 117.95 | 4224.67
46 | Vitrified Flooring Tiles | [8 empty] | 734.46 | 1133.36 | 1029.49 | 782.03 | 3679.34
48 | Vitrified Skirting | [8 empty] | 8.98 | 4.34 |  | 1.21 | 14.53
49 | Ceramic flooring | [10 empty] | 218.26 |  | 218.26
50 | Dado | [10 empty] | 726.45 |  | 726.45
48 | Granite Skirting | [10 empty] | 47.42 | 161.31 | 208.73
41 | Waterproofing for W.C | [10 empty] | 223.39 | 200.78 | 424.17
42 | Waterproofing for terrace | [10 empty] | 15.33 |  | 15.33
51 | Black Granite stone for treads and risers | [11 empty] | 49.32 | 49.32
52 | Granite flooring for steps | [12 empty] | 0
62 | Granite for door frame | [10 empty] | 180.84 |  | 180.84

## CEMENT-2
CEMENT CONSUMPTION STATEMENT
Name of Work:- Construction of sub market at Khedshivapur |  |  |  |  | WO No.:- | जा. क्र. प्रजा/स्थापत्य/उ. बा. खेडशीवापूर/आठ. बाजार/वर्क ऑर्डर/ २०७७/२०१९-२० दि. १९/०९/२०१९
Name of Contractor:- UNIVASTU INDIA LTD |  |  |  |  | Bill No.- | 01
Item No. | Item of work in brief. | Executed Quantity | Therotical rate of consumption of Bitumen/Cement Bag per Unit | Unit | Required as per theoretical calculations. Bag | Remarks.
1 | M-15 Grade | 1911.53 | 6 | Cum | 11469.18 | M.B.No P.No
18 | M-20 Grade | 1005.2 |  | Cum | 0
19 | M-20 Grade | 417.98 |  | Cum | 0
20 | M-20 Grade | 95.07 |  | Cum | 0
| M-20 Grade | 78.7 |  | Cum | 0
| M-20 Grade | 140.44 |  | Cum | 0
| M-20 Grade | 18.73 |  | Cum | 0
| M-20 Grade | 30.1 |  | Cum | 0
| M-20 Grade | 1.23 |  | Cum | 0
| Tremix M-20 Grade | 195.31 |  | Cum | 0
2 | Total M-20 Garde | 1982.76 | 7 | Cum | 13879.32
3 | Tremix M-30 Grade | 343.68 | 8 | Cum | 2749.44
4 | Cement use for other activity like plaster, flooring, eaterproofing etc. |  |  | Cum | 3599.8883
|  |  |  | Total In Bag | 31697.8283 | 1584.8914
M.T.

## Indices
INDICES
Sr. No. | Material | Indices at Tender |  | Current Indices |  | % Above/ Below
A | Labour | 2019-05-01 | 314 | 2025-08-01 | 444.682 | 41.6185
|  | 2019-06-01 | 316 | 2025-09-01 | 444.682 | 40.7222
|  | 2019-07-01 | 319 | 2025-10-01 | 455.63 | 42.8307
|  | Average | 316.3333 |  | 448.3313 | 41.7275
B | Other Material | 2019-05-01 | 121.6 | 2025-08-01 | 155.2 | 27.6316
|  | 2019-06-01 | 121.5 | 2025-09-01 | 155.2 | 27.7366 | 181.5
|  | 2019-07-01 | 121.3 | 2025-10-01 | 155.2 | 27.9472 | 179.8
|  | Average | 121.4667 |  | 155.2 | 27.7717
C | POL | 2019-05-01 | 68.52 | 2025-08-01 | 90.34 | 31.8447
|  | 2019-06-01 | 67.155 | 2025-09-01 | 90.34 | 34.5246
|  | 2019-07-01 | 67.035 | 2025-10-01 | 90.34 | 34.7654
|  | Average | 67.57 |  | 90.34 | 33.6984
D | TMT | 2019-05-01 | 109.4 | 2025-08-01 | 135.2 | 23.5832
|  | 2019-06-01 | 108.4 | 2025-09-01 | 135.6 | 25.0923
|  | 2019-07-01 | 106.1 | 2025-10-01 | 134.4 | 26.673
|  | Average | 107.9667 |  | 135.0667 | 25.1003
E | CEMENT | 2019-05-01 | 123.2 | 2025-08-01 | 130.7 | 6.0877
|  | 2019-06-01 | 122.5 | 2025-09-01 | 130 | 6.1224
|  | 2019-07-01 | 120.6 | 2025-10-01 | 128.5 | 6.5506 |  | 6.5506
|  | Average | 122.1 |  | 129.7333 | 6.2517
26.9099

## Corrected Index
INDICES - Pune | [9 empty] | INDICES - Pune
Sr. No. | Month | INDICES | [7 empty] | Sr. No. | Month | INDICES
|  | Labour |  |  | POL | Other Material | TMT | CEMENT | Structural steel |  |  | Labour | POL | Other Material | TMT | CEMENT | Structural steel
|  | Basic | Linking Factor | Final Indices
| 1 | 2 |  |  | 3 | 4 | 5 | 6 | 7 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | 2013-01-01 | 227 | 1 | 227 | 53.64 | 108 | 100.1 | 103.3 | 104.9 | 1 | 2013-01-01 | 227 | 53.64 | 108 | 100.1 | 103.3 | 104.9
2 | 2013-02-01 | 228 | 1 | 228 | 54.17 | 108.4 | 101.2 | 104.3 | 105.7 | 2 | 2013-02-01 | 228 | 54.17 | 108.4 | 101.2 | 104.3 | 105.7
3 | 2013-03-01 | 227 | 1 | 227 | 54.77 | 108.6 | 99.9 | 103.8 | 108.2 | 3 | 2013-03-01 | 227 | 54.77 | 108.6 | 99.9 | 103.8 | 108.2
4 | 2013-04-01 | 230 | 1 | 230 | 54.77 | 108.6 | 100 | 102.5 | 106.9 | 4 | 2013-04-01 | 230 | 54.77 | 108.6 | 100 | 102.5 | 106.9
5 | 2013-05-01 | 232 | 1 | 232 | 55.95 | 108.6 | 98.9 | 103.6 | 105.7 | 5 | 2013-05-01 | 232 | 55.95 | 108.6 | 98.9 | 103.6 | 105.7
6 | 2013-06-01 | 240 | 1 | 240 | 57.68 | 110.1 | 98.5 | 106 | 106.8 | 6 | 2013-06-01 | 240 | 57.68 | 110.1 | 98.5 | 106 | 106.8
7 | 2013-07-01 | 239 | 1 | 239 | 58.28 | 111.2 | 97.4 | 105.8 | 107.3 | 7 | 2013-07-01 | 239 | 58.28 | 111.2 | 97.4 | 105.8 | 107.3
8 | 2013-08-01 | 244 | 1 | 244 | 58.15 | 112.9 | 96.9 | 103.4 | 107.9 | 8 | 2013-08-01 | 244 | 58.15 | 112.9 | 96.9 | 103.4 | 107.9
9 | 2013-09-01 | 242 | 1 | 242 | 58.83 | 114.3 | 97.7 | 103.5 | 110.2 | 9 | 2013-09-01 | 242 | 58.83 | 114.3 | 97.7 | 103.5 | 110.2
10 | 2013-10-01 | 243 | 1 | 243 | 58.83 | 114.6 | 98.3 | 104.8 | 107 | 10 | 2013-10-01 | 243 | 58.83 | 114.6 | 98.3 | 104.8 | 107
11 | 2013-11-01 | 246 | 1 | 246 | 59.98 | 114.3 | 98.1 | 103.3 | 109.1 | 11 | 2013-11-01 | 246 | 59.98 | 114.3 | 98.1 | 103.3 | 109.1
12 | 2013-12-01 | 246 | 1 | 246 | 60.75 | 113.4 | 98.5 | 102.4 | 107.3 | 12 | 2013-12-01 | 246 | 60.75 | 113.4 | 98.5 | 102.4 | 107.3
13 | 2014-01-01 | 246 | 1 | 246 | 61.33 | 113.6 | 99.5 | 102.6 | 106.6 | 13 | 2014-01-01 | 246 | 61.33 | 113.6 | 99.5 | 102.6 | 106.6
14 | 2014-02-01 | 248 | 1 | 248 | 63.16 | 113.6 | 100.5 | 106.4 | 106.8 | 14 | 2014-02-01 | 248 | 63.16 | 113.6 | 100.5 | 106.4 | 106.8
15 | 2014-03-01 | 248 | 1 | 248 | 63.78 | 114.3 | 101.3 | 107.4 | 107.6 | 15 | 2014-03-01 | 248 | 63.78 | 114.3 | 101.3 | 107.4 | 107.6
16 | 2014-04-01 | 250 | 1 | 250 | 63.78 | 114.1 | 101.8 | 109.8 | 108.3 | 16 | 2014-04-01 | 250 | 63.78 | 114.1 | 101.8 | 109.8 | 108.3
17 | 2014-05-01 | 253 | 1 | 253 | 65.14 | 114.8 | 102.9 | 107.9 | 108.4 | 17 | 2014-05-01 | 253 | 65.14 | 114.8 | 102.9 | 107.9 | 108.4
18 | 2014-06-01 | 252 | 1 | 252 | 65.74 | 115.2 | 104.3 | 110.4 | 107.8 | 18 | 2014-06-01 | 252 | 65.74 | 115.2 | 104.3 | 110.4 | 107.8
19 | 2014-07-01 | 256 | 1 | 256 | 65.99 | 116.7 | 104.1 | 114 | 108.3 | 19 | 2014-07-01 | 256 | 65.99 | 116.7 | 104.1 | 114 | 108.3
20 | 2014-08-01 | 260 | 1 | 260 | 66.895 | 117.2 | 102.2 | 112 | 107.2 | 20 | 2014-08-01 | 260 | 66.895 | 117.2 | 102.2 | 112 | 107.2
21 | 2014-09-01 | 261 | 1 | 261 | 67.24 | 116.4 | 101.9 | 109.5 | 108.3 | 21 | 2014-09-01 | 261 | 67.24 | 116.4 | 101.9 | 109.5 | 108.3
22 | 2014-10-01 | 259 | 1 | 259 | 63.52 | 115.6 | 102.2 | 109.5 | 109.3 | 22 | 2014-10-01 | 259 | 63.52 | 115.6 | 102.2 | 109.5 | 109.3
23 | 2014-11-01 | 258 | 1 | 258 | 61.27 | 114.1 | 100.6 | 106.7 | 109 | 23 | 2014-11-01 | 258 | 61.27 | 114.1 | 100.6 | 106.7 | 109
24 | 2014-12-01 | 258 | 1 | 258 | 58.965 | 112.1 | 99 | 107.9 | 112.1 | 24 | 2014-12-01 | 258 | 58.965 | 112.1 | 99 | 107.9 | 112.1
25 | 2015-01-01 | 259 | 1 | 259 | 55.46 | 110.8 | 98.5 | 112 | 109.8 | 25 | 2015-01-01 | 259 | 55.46 | 110.8 | 98.5 | 112 | 109.8
26 | 2015-02-01 | 259 | 1 | 259 | 53.065 | 109.6 | 96.8 | 110.2 | 112.1 | 26 | 2015-02-01 | 259 | 53.065 | 109.6 | 96.8 | 110.2 | 112.1
27 | 2015-03-01 | 261 | 1 | 261 | 56.26 | 109.9 | 95 | 110.7 | 114.1 | 27 | 2015-03-01 | 261 | 56.26 | 109.9 | 95 | 110.7 | 114.1
28 | 2015-04-01 | 260 | 1 | 260 | 54.995 | 110.2 | 94.7 | 108.3 | 110.6 | 28 | 2015-04-01 | 260 | 54.995 | 110.2 | 94.7 | 108.3 | 110.6
29 | 2015-05-01 | 264 | 1 | 264 | 58.26 | 111.4 | 92.7 | 105.8 | 110.6 | 29 | 2015-05-01 | 264 | 58.26 | 111.4 | 92.7 | 105.8 | 110.6
30 | 2015-06-01 | 266 | 1 | 266 | 58.52 | 111.8 | 91.1 | 105.2 | 109.9 | 30 | 2015-06-01 | 266 | 58.52 | 111.8 | 91.1 | 105.2 | 109.9
31 | 2015-07-01 | 265 | 1 | 265 | 57.57 | 111.1 | 89 | 106.6 | 109 | 31 | 2015-07-01 | 265 | 57.57 | 111.1 | 89 | 106.6 | 109
32 | 2015-08-01 | 265 | 1 | 265 | 50.895 | 110 | 86.5 | 107.4 | 110.2 | 32 | 2015-08-01 | 265 | 50.895 | 110 | 86.5 | 107.4 | 110.2
33 | 2015-09-01 | 271 | 1 | 271 | 49.81 | 109.9 | 86.7 | 110.3 | 111.6 | 33 | 2015-09-01 | 271 | 49.81 | 109.9 | 86.7 | 110.3 | 111.6
34 | 2015-10-01 | 275 | 1 | 275 | 49.81 | 110.1 | 85.3 | 110.1 | 109.7 | 34 | 2015-10-01 | 275 | 49.81 | 110.1 | 85.3 | 110.1 | 109.7
35 | 2015-11-01 | 273 | 1 | 273 | 50.68 | 109.9 | 83.5 | 109 | 110.1 | 35 | 2015-11-01 | 273 | 50.68 | 109.9 | 83.5 | 109 | 110.1
36 | 2015-12-01 | 272 | 1 | 272 | 50.3 | 109.4 | 83.1 | 107 | 109.8 | 36 | 2015-12-01 | 272 | 50.3 | 109.4 | 83.1 | 107 | 109.8
37 | 2016-01-01 | 273 | 1 | 273 | 50 | 108 | 83.2 | 104.5 | 110.5 | 37 | 2016-01-01 | 273 | 50 | 108 | 83.2 | 104.5 | 110.5
38 | 2016-02-01 | 269 | 1 | 269 | 50.105 | 107.1 | 83 | 103.6 | 110.1 | 38 | 2016-02-01 | 269 | 50.105 | 107.1 | 83 | 103.6 | 110.1
39 | 2016-03-01 | 270 | 1 | 270 | 52.735 | 107.7 | 84.9 | 106 | 109.9 | 39 | 2016-03-01 | 270 | 52.735 | 107.7 | 84.9 | 106 | 109.9
40 | 2016-04-01 | 275 | 1 | 275 | 53.445 | 109 | 86 | 106.3 | 106.8 | 40 | 2016-04-01 | 275 | 53.445 | 109 | 86 | 106.3 | 106.8
41 | 2016-05-01 | 275 | 1 | 275 | 55.275 | 110.4 | 86.1 | 107.8 | 105.6 | 41 | 2016-05-01 | 275 | 55.275 | 110.4 | 86.1 | 107.8 | 105.6
42 | 2016-06-01 | 281 | 1 | 281 | 58.67 | 111.7 | 84.4 | 109 | 103.9 | 42 | 2016-06-01 | 281 | 58.67 | 111.7 | 84.4 | 109 | 103.9
43 | 2016-07-01 | 286 | 1 | 286 | 58.34 | 111.8 | 83.1 | 109.4 | 105.2 | 43 | 2016-07-01 | 286 | 58.34 | 111.8 | 83.1 | 109.4 | 105.2
44 | 2016-08-01 | 278 | 1 | 278 | 55.165 | 111.2 | 81.5 | 108.9 | 103.1 | 44 | 2016-08-01 | 278 | 55.165 | 111.2 | 81.5 | 108.9 | 103.1
45 | 2016-09-01 | 277 | 1 | 277 | 56.87 | 111.4 | 82.9 | 110 | 104.4 | 45 | 2016-09-01 | 277 | 56.87 | 111.4 | 82.9 | 110 | 104.4
46 | 2016-10-01 | 280 | 1 | 280 | 58.09 | 111.5 | 83.8 | 109.5 | 105.1 | 46 | 2016-10-01 | 280 | 58.09 | 111.5 | 83.8 | 109.5 | 105.1
47 | 2016-11-01 | 280 | 1 | 280 | 59.75 | 111.9 | 86 | 108.2 | 102 | 47 | 2016-11-01 | 280 | 59.75 | 111.9 | 86 | 108.2 | 102
48 | 2016-12-01 | 276 | 1 | 276 | 59.805 | 111.7 | 86 | 106.4 | 106.3 | 48 | 2016-12-01 | 276 | 59.805 | 111.7 | 86 | 106.4 | 106.3
49 | 2017-01-01 | 273 | 1 | 273 | 62.7 | 112.6 | 86.8 | 105.9 | 109 | 49 | 2017-01-01 | 273 | 62.7 | 112.6 | 86.8 | 105.9 | 109
50 | 2017-02-01 | 271 | 1 | 271 | 63.32 | 113 | 87.1 | 105.7 | 109.5 | 50 | 2017-02-01 | 271 | 63.32 | 113 | 87.1 | 105.7 | 109.5
51 | 2017-03-01 | 273 | 1 | 273 | 63.32 | 113.2 | 89.4 | 106.7 | 109.1 | 51 | 2017-03-01 | 273 | 63.32 | 113.2 | 89.4 | 106.7 | 109.1
52 | 2017-04-01 | 273 | 1 | 273 | 60.42 | 113.2 | 90.8 | 110.5 | 107.5 | 52 | 2017-04-01 | 273 | 60.42 | 113.2 | 90.8 | 110.5 | 107.5
53 | 2017-05-01 | 272 | 1 | 272 | 60.31 | 112.9 | 90.3 | 113.7 | 107.1 | 53 | 2017-05-01 | 272 | 60.31 | 112.9 | 90.3 | 113.7 | 107.1
54 | 2017-06-01 | 274 | 1 | 274 | 58.81 | 112.7 | 89.8 | 112.9 | 106.9 | 54 | 2017-06-01 | 274 | 58.81 | 112.7 | 89.8 | 112.9 | 106.9
55 | 2017-07-01 | 276 | 1 | 276 | 57.565 | 113.9 | 91.6 | 111.3 | 108.2 | 55 | 2017-07-01 | 276 | 57.565 | 113.9 | 91.6 | 111.3 | 108.2
56 | 2017-08-01 | 277 | 1 | 277 | 58.9 | 114.8 | 92 | 111.1 | 107 | 56 | 2017-08-01 | 277 | 58.9 | 114.8 | 92 | 111.1 | 107
57 | 2017-09-01 | 276 | 1 | 276 | 60.64 | 114.9 | 92.5 | 110.9 | 109.2 | 57 | 2017-09-01 | 276 | 60.64 | 114.9 | 92.5 | 110.9 | 109.2
58 | 2017-10-01 | 278 | 1 | 278 | 60.48 | 115.6 | 91.7 | 109.2 | 106.2 | 58 | 2017-10-01 | 278 | 60.48 | 115.6 | 91.7 | 109.2 | 106.2
59 | 2017-11-01 | 279 | 1 | 279 | 59.955 | 116.4 | 95.4 | 110.2 | 108.3 | 59 | 2017-11-01 | 279 | 59.955 | 116.4 | 95.4 | 110.2 | 108.3
60 | 2017-12-01 | 279 | 1 | 279 | 61.005 | 115.7 | 98.5 | 111 | 109.7 | 60 | 2017-12-01 | 279 | 61.005 | 115.7 | 98.5 | 111 | 109.7
61 | 2018-01-01 | 289 | 1 | 289 | 64.655 | 116 | 102.9 | 111.2 | 112.8 | 61 | 2018-01-01 | 289 | 64.655 | 116 | 102.9 | 111.2 | 112.8
62 | 2018-02-01 | 289 | 1 | 289 | 66.055 | 116.1 | 105.9 | 113.2 | 114.7 | 62 | 2018-02-01 | 289 | 66.055 | 116.1 | 105.9 | 113.2 | 114.7
63 | 2018-03-01 | 292 | 1 | 292 | 66.19 | 116.3 | 105.9 | 111.8 | 114.2 | 63 | 2018-03-01 | 292 | 66.19 | 116.3 | 105.9 | 111.8 | 114.2
64 | 2018-04-01 | 293 | 1 | 293 | 68.36 | 117.3 | 108 | 113.1 | 111.8 | 64 | 2018-04-01 | 293 | 68.36 | 117.3 | 108 | 113.1 | 111.8
65 | 2018-05-01 | 298 | 1 | 298 | 70.84 | 118.3 | 109.8 | 113 | 112.9 | 65 | 2018-05-01 | 298 | 70.84 | 118.3 | 109.8 | 113 | 112.9
66 | 2018-06-01 | 300 | 1 | 300 | 71.345 | 119.1 | 110.8 | 111.6 | 113.9 | 66 | 2018-06-01 | 300 | 71.345 | 119.1 | 110.8 | 111.6 | 113.9
67 | 2018-07-01 | 317 | 1 | 317 | 70.525 | 119.9 | 110.5 | 113 | 115.8 | 67 | 2018-07-01 | 317 | 70.525 | 119.9 | 110.5 | 113 | 115.8
68 | 2018-08-01 | 314 | 1 | 314 | 72.08 | 120.1 | 108.2 | 111.1 | 118.6 | 68 | 2018-08-01 | 314 | 72.08 | 120.1 | 108.2 | 111.1 | 118.6
69 | 2018-09-01 | 317 | 1 | 317 | 76.165 | 120.9 | 112.3 | 111.4 | 120 | 69 | 2018-09-01 | 317 | 76.165 | 120.9 | 112.3 | 111.4 | 120
70 | 2018-10-01 | 320 | 1 | 320 | 77.155 | 121.1 | 111.5 | 110.7 |  | 70 | 2018-10-01 | 320 | 77.155 | 121.1 | 111.5 | 110.7
71 | 2018-11-01 | 319 | 1 | 319 | 72.775 | 121.6 | 112.3 | 110.3 |  | 71 | 2018-11-01 | 319 | 72.775 | 121.6 | 112.3 | 110.3
72 | 2018-12-01 | 320 | 1 | 320 | 66.965 | 119.7 | 110.3 | 111.5 |  | 72 | 2018-12-01 | 320 | 66.965 | 119.7 | 110.3 | 111.5
73 | 2019-01-01 | 307 | 1 | 307 | 66.115 | 119.2 | 109.5 | 112.7 |  | 73 | 2019-01-01 | 307 | 66.115 | 119.2 | 109.5 | 112.7
74 | 2019-02-01 | 307 | 1 | 307 | 68.23 | 119.5 | 109.9 | 116.1 |  | 74 | 2019-02-01 | 307 | 68.23 | 119.5 | 109.9 | 116.1
75 | 2019-03-01 | 309 | 1 | 309 | 68.625 | 119.9 | 110.1 | 116.4 |  | 75 | 2019-03-01 | 309 | 68.625 | 119.9 | 110.1 | 116.4
76 | 2019-04-01 | 312 | 1 | 312 | 68.33 | 121.1 | 110.1 | 119.6 |  | 76 | 2019-04-01 | 312 | 68.33 | 121.1 | 110.1 | 119.6
77 | 2019-05-01 | 314 | 1 | 314 | 68.52 | 121.6 | 109.4 | 123.2 |  | 1 | 2019-05-01 | 314 | 68.52 | 121.6 | 109.4 | 123.2
78 | 2019-06-01 | 316 | 1 | 316 | 67.155 | 121.5 | 108.4 | 122.5 |  | 2 | 2019-06-01 | 316 | 67.155 | 121.5 | 108.4 | 122.5
79 | 2019-07-01 | 319 | 1 | 319 | 67.035 | 121.3 | 106.1 | 120.6 |  | 3 | 2019-07-01 | 319 | 67.035 | 121.3 | 106.1 | 120.6
80 | 2019-08-01 | 320 | 1 | 320 | 67.49 | 121.5 | 104.2 | 118.5 |  | 4 | 2019-08-01 | 320 | 67.49 | 121.5 | 104.2 | 118.5
81 | 2019-09-01 | 322 | 1 | 322 | 68.185 | 121.3 | 103.4 | 120.7 |  | 5 | 2019-09-01 | 322 | 68.185 | 121.3 | 103.4 | 120.7
82 | 2019-10-01 | 325 | 1 | 325 | 68.63 | 122 | 102.6 | 118.6 |  | 6 | 2019-10-01 | 325 | 68.63 | 122 | 102.6 | 118.6
83 | 2019-11-01 | 328 | 1 | 328 | 67.66 | 122.3 | 101.9 | 119.6 |  | 7 | 2019-11-01 | 328 | 67.66 | 122.3 | 101.9 | 119.6
84 | 2019-12-01 | 330 | 1 | 330 | 68.845 | 122.8 | 103.1 | 119.2 |  | 8 | 2019-12-01 | 330 | 68.845 | 122.8 | 103.1 | 119.2
85 | 2020-01-01 | 330 | 1 | 330 | 69.17 | 123.4 | 104.9 | 118 |  | 9 | 2020-01-01 | 330 | 69.17 | 123.4 | 104.9 | 118
86 | 2020-02-01 | 328 | 1 | 328 | 67.2 | 122.2 | 105.6 | 119.8 |  | 10 | 2020-02-01 | 328 | 67.2 | 122.2 | 105.6 | 119.8
87 | 2020-03-01 | 326 | 1 | 326 | 65.02 | 120.4 | 106.6 | 119.7 |  | 11 | 2020-03-01 | 326 | 65.02 | 120.4 | 106.6 | 119.7
88 | 2020-04-01 | 329 | 1 | 329 | 64.98 | 119.2 | 106.2 | 123.3 |  | 12 | 2020-04-01 | 329 | 64.98 | 119.2 | 106.2 | 123.3
89 | 2020-05-01 | 330 | 1 | 330 | 64.98 | 117.5 | 105.6 | 124.6 |  | 13 | 2020-05-01 | 330 | 64.98 | 117.5 | 105.6 | 124.6
90 | 2020-06-01 | 332 | 1 | 332 | 72.17 | 119.3 | 104.8 | 123.2 |  | 14 | 2020-06-01 | 332 | 72.17 | 119.3 | 104.8 | 123.2
91 | 2020-07-01 | 336 | 1 | 336 | 78.135 | 121 | 102.8 | 121.5 |  | 15 | 2020-07-01 | 336 | 78.135 | 121 | 102.8 | 121.5
92 | 2020-08-01 | 338 | 1 | 338 | 78.67 | 122 | 104.5 | 119.7 |  | 16 | 2020-08-01 | 338 | 78.67 | 122 | 104.5 | 119.7
93 | 2020-09-01 | 114.7 | 3.22 | 369.334 | 77.09 | 122.9 | 106.3 | 118.3 |  | 17 | 2020-09-01 | 369.334 | 77.09 | 122.9 | 106.3 | 118.3
94 | 2020-10-01 | 115.3 | 3.22 | 371.266 | 75.525 | 123.6 | 108 | 117.8 |  | 18 | 2020-10-01 | 371.266 | 75.525 | 123.6 | 108 | 117.8
95 | 2020-11-01 | 115.8 | 3.22 | 372.876 | 76.59 | 125.1 | 112.8 | 118.7 |  | 19 | 2020-11-01 | 372.876 | 76.59 | 125.1 | 112.8 | 118.7
96 | 2020-12-01 | 115.4 | 3.22 | 371.588 | 78.34 | 125.4 | 118.2 | 118.1 |  | 20 | 2020-12-01 | 371.588 | 78.34 | 125.4 | 118.2 | 118.1
97 | 2021-01-01 | 115.5 | 3.22 | 371.91 | 80.485 | 126.5 | 125.6 | 118.5 |  | 21 | 2021-01-01 | 371.91 | 80.485 | 126.5 | 125.6 | 118.5
98 | 2021-02-01 | 116.3 | 3.22 | 374.486 | 84.475 | 128.1 | 124.7 | 120.6 |  | 22 | 2021-02-01 | 374.486 | 84.475 | 128.1 | 124.7 | 120.6
99 | 2021-03-01 | 117.1 | 3.22 | 377.062 | 86.48 | 129.9 | 124.6 | 125 |  | 23 | 2021-03-01 | 377.062 | 86.48 | 129.9 | 124.6 | 125
100 | 2021-04-01 | 117.9 | 3.22 | 379.638 | 86.11 | 132 | 127.6 | 125.7 |  | 24 | 2021-04-01 | 379.638 | 86.11 | 132 | 127.6 | 125.7
101 | 2021-05-01 | 117.1 | 3.22 | 377.062 | 88.515 | 132.9 | 130.9 | 123.6 |  | 25 | 2021-05-01 | 377.062 | 88.515 | 132.9 | 130.9 | 123.6
102 | 2021-06-01 | 119.1 | 3.22 | 383.502 | 92.915 | 133.7 | 131.7 | 123.6 |  | 26 | 2021-06-01 | 383.502 | 92.915 | 133.7 | 131.7 | 123.6
103 | 2021-07-01 | 120.8 | 3.22 | 388.976 | 95.335 | 135 | 131.4 | 124.7 |  | 27 | 2021-07-01 | 388.976 | 95.335 | 135 | 131.4 | 124.7
104 | 2021-08-01 | 120.4 | 3.22 | 387.688 | 94.915 | 136.2 | 132.9 | 123.3 |  | 28 | 2021-08-01 | 387.688 | 94.915 | 136.2 | 132.9 | 123.3
105 | 2021-09-01 | 119.9 | 3.22 | 386.078 | 95.025 | 137.4 | 133.6 | 122.6 |  | 29 | 2021-09-01 | 386.078 | 95.025 | 137.4 | 133.6 | 122.6
106 | 2021-10-01 | 121.1 | 3.22 | 389.942 | 99.975 | 140.7 | 140.8 | 125.3 |  | 30 | 2021-10-01 | 389.942 | 99.975 | 140.7 | 140.8 | 125.3
107 | 2021-11-01 | 121.5 | 3.22 | 391.23 | 98.38 | 143.7 | 140.4 | 127.7 |  | 31 | 2021-11-01 | 391.23 | 98.38 | 143.7 | 140.4 | 127.7
108 | 2021-12-01 | 120.9 | 3.22 | 389.298 | 92.3 | 143.3 | 139 | 125.5 |  | 32 | 2021-12-01 | 389.298 | 92.3 | 143.3 | 139 | 125.5
109 | 2022-01-01 | 120.8 | 3.22 | 388.976 | 92.3 | 143.8 | 139.9 | 124.3 |  | 33 | 2022-01-01 | 388.976 | 92.3 | 143.8 | 139.9 | 124.3
110 | 2022-02-01 | 121 | 3.22 | 389.62 | 92.3 | 145.3 | 144.8 | 127.9 |  | 34 | 2022-02-01 | 389.62 | 92.3 | 145.3 | 144.8 | 127.9
111 | 2022-03-01 | 121.5 | 3.22 | 391.23 | 95.615 | 148.9 | 155.9 | 130.1 |  | 35 | 2022-03-01 | 391.23 | 95.615 | 148.9 | 155.9 | 130.1
112 | 2022-04-01 | 122.4 | 3.22 | 394.128 | 100.795 | 152.3 | 159.1 | 133.5 |  | 36 | 2022-04-01 | 394.128 | 100.795 | 152.3 | 159.1 | 133.5
113 | 2022-05-01 | 123.2 | 3.22 | 396.704 | 99.005 | 155 | 156.7 | 135.1 |  | 37 | 2022-05-01 | 396.704 | 99.005 | 155 | 156.7 | 135.1
114 | 2022-06-01 | 123.3 | 3.22 | 397.026 | 95.35 | 155.4 | 151.6 | 138 |  | 38 | 2022-06-01 | 397.026 | 95.35 | 155.4 | 151.6 | 138
115 | 2022-07-01 | 123.2 | 3.22 | 396.704 | 93.85 | 154 | 149.9 | 135 |  | 39 | 2022-07-01 | 396.704 | 93.85 | 154 | 149.9 | 135
116 | 2022-08-01 | 123 | 3.22 | 396.06 | 92.35 | 153.2 | 149.4 | 133.8 |  | 40 | 2022-08-01 | 396.06 | 92.35 | 153.2 | 149.4 | 133.8
117 | 2022-09-01 | 122.8 | 3.22 | 395.416 | 92.35 | 151.9 | 146.8 | 133.4 |  | 41 | 2022-09-01 | 395.416 | 92.35 | 151.9 | 146.8 | 133.4
118 | 2022-10-01 | 124.2 | 3.22 | 399.924 | 92.35 | 152.9 | 147.9 | 133.5 |  | 42 | 2022-10-01 | 399.924 | 92.35 | 152.9 | 147.9 | 133.5
119 | 2022-11-01 | 122.3 | 3.22 | 393.806 | 92.35 | 152.1 | 145 | 134.5 |  | 43 | 2022-11-01 | 393.806 | 92.35 | 152.1 | 145 | 134.5
120 | 2022-12-01 | 122.4 | 3.22 | 394.128 | 92.35 | 150.4 | 145.7 | 135 |  | 44 | 2022-12-01 | 394.128 | 92.35 | 150.4 | 145.7 | 135
121 | 2023-01-01 | 123.4 | 3.22 | 397.348 | 92.35 | 150.7 | 148.3 | 136.6 |  | 45 | 2023-01-01 | 397.348 | 92.35 | 150.7 | 148.3 | 136.6
122 | 2023-02-01 | 123.4 | 3.22 | 397.348 | 92.35 | 150.9 | 148.4 | 136.5 |  | 46 | 2023-02-01 | 397.348 | 92.35 | 150.9 | 148.4 | 136.5
123 | 2023-03-01 | 124.3 | 3.22 | 400.246 | 92.35 | 151 | 147.6 | 136.8 |  | 47 | 2023-03-01 | 400.246 | 92.35 | 151 | 147.6 | 136.8
124 | 2023-04-01 | 124.3 | 3.22 | 400.246 | 92.35 | 151.1 | 145.7 | 136 |  | 48 | 2023-04-01 | 400.246 | 92.35 | 151.1 | 145.7 | 136
125 | 2023-05-01 | 125 | 3.22 | 402.5 | 92.35 | 149.4 | 144.4 | 134.7 |  | 49 | 2023-05-01 | 402.5 | 92.35 | 149.4 | 144.4 | 134.7
126 | 2023-06-01 | 126.3 | 3.22 | 406.686 | 92.35 | 148.9 | 141.7 | 135 |  | 50 | 2023-06-01 | 406.686 | 92.35 | 148.9 | 141.7 | 135
127 | 2023-07-01 | 127.4 | 3.22 | 410.228 | 92.35 | 152.1 | 139.5 | 135.6 |  | 51 | 2023-07-01 | 410.228 | 92.35 | 152.1 | 139.5 | 135.6
128 | 2023-08-01 | 127.1 | 3.22 | 409.262 | 92.35 | 152.5 | 140.8 | 136.2 |  | 52 | 2023-08-01 | 409.262 | 92.35 | 152.5 | 140.8 | 136.2
129 | 2023-09-01 | 125 | 3.22 | 402.5 | 92.35 | 151.8 | 143.8 | 134.9 |  | 53 | 2023-09-01 | 402.5 | 92.35 | 151.8 | 143.8 | 134.9
130 | 2023-10-01 | 128.1 | 3.22 | 412.482 | 92.35 | 152.5 | 143.1 | 136.7 |  | 54 | 2023-10-01 | 412.482 | 92.35 | 152.5 | 143.1 | 136.7
131 | 2023-11-01 | 127.3 | 3.22 | 409.906 | 92.35 | 153.1 | 143.2 | 135.3 |  | 55 | 2023-11-01 | 409.906 | 92.35 | 153.1 | 143.2 | 135.3
132 | 2023-12-01 | 127.1 | 3.22 | 409.262 | 92.35 | 151.8 | 139.7 | 135.9 |  | 56 | 2023-12-01 | 409.262 | 92.35 | 151.8 | 139.7 | 135.9
133 | 2024-01-01 | 127.6 | 3.22 | 410.872 | 92.35 | 151.2 | 138.3 | 135.5 |  | 57 | 2024-01-01 | 410.872 | 92.35 | 151.2 | 138.3 | 135.5
134 | 2024-02-01 | 129.6 | 3.22 | 417.312 | 92.35 | 151.2 | 138.3 | 134.1 |  | 58 | 2024-02-01 | 417.312 | 92.35 | 151.2 | 138.3 | 134.1
135 | 2024-03-01 | 128.1 | 3.22 | 412.482 | 91.315 | 151.4 | 138.9 | 132 |  | 59 | 2024-03-01 | 412.482 | 91.315 | 151.4 | 138.9 | 132
136 | 2024-04-01 | 127.8 | 3.22 | 411.516 | 90.28 | 152.9 | 142.3 | 131.1 |  | 60 | 2024-04-01 | 411.516 | 90.28 | 152.9 | 142.3 | 131.1
137 | 2024-05-01 | 129.2 | 3.22 | 416.024 | 90.28 | 153.5 | 144.5 | 129.3 |  | 61 | 2024-05-01 | 416.024 | 90.28 | 153.5 | 144.5 | 129.3
138 | 2024-06-01 | 129.4 | 3.22 | 416.668 | 90.28 | 154 | 143.6 | 126.8 |  | 62 | 2024-06-01 | 416.668 | 90.28 | 154 | 143.6 | 126.8
139 | 2024-07-01 | 130.8 | 3.22 | 421.176 | 90.28 | 155.3 | 139.7 | 124 |  | 63 | 2024-07-01 | 421.176 | 90.28 | 155.3 | 139.7 | 124
140 | 2024-08-01 | 131.1 | 3.22 | 422.142 | 90.28 | 154.4 | 138.6 | 122.6 |  | 64 | 2024-08-01 | 422.142 | 90.28 | 154.4 | 138.6 | 122.6
141 | 2024-09-01 | 131.1 | 3.22 | 422.142 | 90.28 | 154.7 | 138.9 | 125 |  | 65 | 2024-09-01 | 422.142 | 90.28 | 154.7 | 138.9 | 125
142 | 2024-10-01 | 131.7 | 3.22 | 424.074 | 90.28 | 156.7 | 140 | 124.6 |  | 66 | 2024-10-01 | 424.074 | 90.28 | 156.7 | 140 | 124.6
143 | 2024-11-01 | 132.5 | 3.22 | 426.65 | 90.28 | 156.4 | 140.2 | 125.3 |  | 67 | 2024-11-01 | 426.65 | 90.28 | 156.4 | 140.2 | 125.3
144 | 2024-12-01 | 132.8 | 3.22 | 427.616 | 90.31 | 155.7 | 139.5 | 127.9 |  | 68 | 2024-12-01 | 427.616 | 90.31 | 155.7 | 139.5 | 127.9
145 | 2025-01-01 | 133.9 | 3.22 | 431.158 | 90.34 | 155 | 138.5 | 128.2 |  | 69 | 2025-01-01 | 431.158 | 90.34 | 155 | 138.5 | 128.2
146 | 2025-02-01 | 134 | 3.22 | 431.48 | 90.34 | 154.9 | 138.7 | 128.9 |  | 70 | 2025-02-01 | 431.48 | 90.34 | 154.9 | 138.7 | 128.9
147 | 2025-03-01 | 133.9 | 3.22 | 431.158 | 90.34 | 154.8 | 140 | 129.3 |  | 71 | 2025-03-01 | 431.158 | 90.34 | 154.8 | 140 | 129.3
148 | 2025-04-01 | 134 | 3.22 | 431.48 | 90.34 | 154.2 | 140.8 | 127.6 |  | 72 | 2025-04-01 | 431.48 | 90.34 | 154.2 | 140.8 | 127.6
149 | 2025-05-01 | 135.3 | 3.22 | 435.666 | 90.34 | 153.7 | 138.7 | 131 |  | 73 | 2025-05-01 | 435.666 | 90.34 | 153.7 | 138.7 | 131
150 | 2025-06-01 | 135.4 | 3.22 | 435.988 | 90.34 | 153.7 | 137.2 | 131.3 |  | 74 | 2025-06-01 | 435.988 | 90.34 | 153.7 | 137.2 | 131.3
151 | 2025-07-01 | 137.2 | 3.22 | 441.784 | 90.34 | 154.4 | 135.4 | 131.4 |  | 75 | 2025-07-01 | 441.784 | 90.34 | 154.4 | 135.4 | 131.4
152 | 2025-08-01 | 138.1 | 3.22 | 444.682 | 90.34 | 155.2 | 135.8 | 131 |  | 76 | 2025-08-01 | 444.682 | 90.34 | 155.2 | 135.8 | 131
153 | 2025-09-01 | 138.1 | 3.22 | 444.682 | 90.34 | 155.2 | 135.8 | 131 |  | 77 | 2025-09-01 | 444.682 | 90.34 | 155.2 | 135.8 | 131

## Corrected Index (2)
INDICES - Pune | [7 empty] | INDICES - Pune
Sr. No. | Month | INDICES | [5 empty] | Sr. No. | Month | INDICES
|  | Labour | POL | Other Material | TMT | CEMENT | Structural steel |  |  | Labour | POL | Other Material | TMT | CEMENT | Structural steel
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | 2019-05-01 | 314 | 68.52 | 121.6 | 109.4 | 123.2 |  | 1 | 2019-05-01 | 314 | 68.52 | 121.6 | 109.4 | 123.2
2 | 2019-06-01 | 316 | 67.155 | 121.5 | 108.4 | 122.5 |  | 2 | 2019-06-01 | 316 | 67.155 | 121.5 | 108.4 | 122.5
3 | 2019-07-01 | 319 | 67.035 | 121.3 | 106.1 | 120.6 |  | 3 | 2019-07-01 | 319 | 67.035 | 121.3 | 106.1 | 120.6
4 | 2019-08-01 | 320 | 67.49 | 121.5 | 104.2 | 118.5 |  | 4 | 2019-08-01 | 320 | 67.49 | 121.5 | 104.2 | 118.5
5 | 2019-09-01 | 322 | 68.185 | 121.3 | 103.4 | 120.7 |  | 5 | 2019-09-01 | 322 | 68.185 | 121.3 | 103.4 | 120.7
6 | 2019-10-01 | 325 | 68.63 | 122 | 102.6 | 118.6 |  | 6 | 2019-10-01 | 325 | 68.63 | 122 | 102.6 | 118.6
7 | 2019-11-01 | 328 | 67.66 | 122.3 | 101.9 | 119.6 |  | 7 | 2019-11-01 | 328 | 67.66 | 122.3 | 101.9 | 119.6
8 | 2019-12-01 | 330 | 68.845 | 122.8 | 103.1 | 119.2 |  | 8 | 2019-12-01 | 330 | 68.845 | 122.8 | 103.1 | 119.2
9 | 2020-01-01 | 330 | 69.17 | 123.4 | 104.9 | 118 |  | 9 | 2020-01-01 | 330 | 69.17 | 123.4 | 104.9 | 118
10 | 2020-02-01 | 328 | 67.2 | 122.2 | 105.6 | 119.8 |  | 10 | 2020-02-01 | 328 | 67.2 | 122.2 | 105.6 | 119.8
11 | 2020-03-01 | 326 | 65.02 | 120.4 | 106.6 | 119.7 |  | 11 | 2020-03-01 | 326 | 65.02 | 120.4 | 106.6 | 119.7
12 | 2020-04-01 | 329 | 64.98 | 119.2 | 106.2 | 123.3 |  | 12 | 2020-04-01 | 329 | 64.98 | 119.2 | 106.2 | 123.3
13 | 2020-05-01 | 330 | 64.98 | 117.5 | 105.6 | 124.6 |  | 13 | 2020-05-01 | 330 | 64.98 | 117.5 | 105.6 | 124.6
14 | 2020-06-01 | 332 | 72.17 | 119.3 | 104.8 | 123.2 |  | 14 | 2020-06-01 | 332 | 72.17 | 119.3 | 104.8 | 123.2
15 | 2020-07-01 | 336 | 78.135 | 121 | 102.8 | 121.5 |  | 15 | 2020-07-01 | 336 | 78.135 | 121 | 102.8 | 121.5
16 | 2020-08-01 | 338 | 78.67 | 122 | 104.5 | 119.7 |  | 16 | 2020-08-01 | 338 | 78.67 | 122 | 104.5 | 119.7
17 | 2020-09-01 | 369.334 | 77.09 | 122.9 | 106.3 | 118.3 |  | 17 | 2020-09-01 | 369.334 | 77.09 | 122.9 | 106.3 | 118.3
18 | 2020-10-01 | 371.266 | 75.525 | 123.6 | 108 | 117.8 |  | 18 | 2020-10-01 | 371.266 | 75.525 | 123.6 | 108 | 117.8
19 | 2020-11-01 | 372.876 | 76.59 | 125.1 | 112.8 | 118.7 |  | 19 | 2020-11-01 | 372.876 | 76.59 | 125.1 | 112.8 | 118.7
20 | 2020-12-01 | 371.588 | 78.34 | 125.4 | 118.2 | 118.1 |  | 20 | 2020-12-01 | 371.588 | 78.34 | 125.4 | 118.2 | 118.1
21 | 2021-01-01 | 371.91 | 80.485 | 126.5 | 125.6 | 118.5 |  | 21 | 2021-01-01 | 371.91 | 80.485 | 126.5 | 125.6 | 118.5
22 | 2021-02-01 | 374.486 | 84.475 | 128.1 | 124.7 | 120.6 |  | 22 | 2021-02-01 | 374.486 | 84.475 | 128.1 | 124.7 | 120.6
23 | 2021-03-01 | 377.062 | 86.48 | 129.9 | 124.6 | 125 |  | 23 | 2021-03-01 | 377.062 | 86.48 | 129.9 | 124.6 | 125
24 | 2021-04-01 | 379.638 | 86.11 | 132 | 127.6 | 125.7 |  | 24 | 2021-04-01 | 379.638 | 86.11 | 132 | 127.6 | 125.7
25 | 2021-05-01 | 377.062 | 88.515 | 132.9 | 130.9 | 123.6 |  | 25 | 2021-05-01 | 377.062 | 88.515 | 132.9 | 130.9 | 123.6
26 | 2021-06-01 | 383.502 | 92.915 | 133.7 | 131.7 | 123.6 |  | 26 | 2021-06-01 | 383.502 | 92.915 | 133.7 | 131.7 | 123.6
27 | 2021-07-01 | 388.976 | 95.335 | 135 | 131.4 | 124.7 |  | 27 | 2021-07-01 | 388.976 | 95.335 | 135 | 131.4 | 124.7
28 | 2021-08-01 | 387.688 | 94.915 | 136.2 | 132.9 | 123.3 |  | 28 | 2021-08-01 | 387.688 | 94.915 | 136.2 | 132.9 | 123.3
29 | 2021-09-01 | 386.078 | 95.025 | 137.4 | 133.6 | 122.6 |  | 29 | 2021-09-01 | 386.078 | 95.025 | 137.4 | 133.6 | 122.6
30 | 2021-10-01 | 389.942 | 99.975 | 140.7 | 140.8 | 125.3 |  | 30 | 2021-10-01 | 389.942 | 99.975 | 140.7 | 140.8 | 125.3
31 | 2021-11-01 | 391.23 | 98.38 | 143.7 | 140.4 | 127.7 |  | 31 | 2021-11-01 | 391.23 | 98.38 | 143.7 | 140.4 | 127.7
32 | 2021-12-01 | 389.298 | 92.3 | 143.3 | 139 | 125.5 |  | 32 | 2021-12-01 | 389.298 | 92.3 | 143.3 | 139 | 125.5
33 | 2022-01-01 | 388.976 | 92.3 | 143.8 | 139.9 | 124.3 |  | 33 | 2022-01-01 | 388.976 | 92.3 | 143.8 | 139.9 | 124.3
34 | 2022-02-01 | 389.62 | 92.3 | 145.3 | 144.8 | 127.9 |  | 34 | 2022-02-01 | 389.62 | 92.3 | 145.3 | 144.8 | 127.9
35 | 2022-03-01 | 391.23 | 95.615 | 148.9 | 155.9 | 130.1 |  | 35 | 2022-03-01 | 391.23 | 95.615 | 148.9 | 155.9 | 130.1
36 | 2022-04-01 | 394.128 | 100.795 | 152.3 | 159.1 | 133.5 |  | 36 | 2022-04-01 | 394.128 | 100.795 | 152.3 | 159.1 | 133.5
37 | 2022-05-01 | 396.704 | 99.005 | 155 | 156.7 | 135.1 |  | 37 | 2022-05-01 | 396.704 | 99.005 | 155 | 156.7 | 135.1
38 | 2022-06-01 | 397.026 | 95.35 | 155.4 | 151.6 | 138 |  | 38 | 2022-06-01 | 397.026 | 95.35 | 155.4 | 151.6 | 138
39 | 2022-07-01 | 396.704 | 93.85 | 154 | 149.9 | 135 |  | 39 | 2022-07-01 | 396.704 | 93.85 | 154 | 149.9 | 135
40 | 2022-08-01 | 396.06 | 92.35 | 153.2 | 149.4 | 133.8 |  | 40 | 2022-08-01 | 396.06 | 92.35 | 153.2 | 149.4 | 133.8
41 | 2022-09-01 | 395.416 | 92.35 | 151.9 | 146.8 | 133.4 |  | 41 | 2022-09-01 | 395.416 | 92.35 | 151.9 | 146.8 | 133.4
42 | 2022-10-01 | 399.924 | 92.35 | 152.9 | 147.9 | 133.5 |  | 42 | 2022-10-01 | 399.924 | 92.35 | 152.9 | 147.9 | 133.5
43 | 2022-11-01 | 393.806 | 92.35 | 152.1 | 145 | 134.5 |  | 43 | 2022-11-01 | 393.806 | 92.35 | 152.1 | 145 | 134.5
44 | 2022-12-01 | 394.128 | 92.35 | 150.4 | 145.7 | 135 |  | 44 | 2022-12-01 | 394.128 | 92.35 | 150.4 | 145.7 | 135
45 | 2023-01-01 | 397.348 | 92.35 | 150.7 | 148.3 | 136.6 |  | 45 | 2023-01-01 | 397.348 | 92.35 | 150.7 | 148.3 | 136.6
46 | 2023-02-01 | 397.348 | 92.35 | 150.9 | 148.4 | 136.5 |  | 46 | 2023-02-01 | 397.348 | 92.35 | 150.9 | 148.4 | 136.5
47 | 2023-03-01 | 400.246 | 92.35 | 151 | 147.6 | 136.8 |  | 47 | 2023-03-01 | 400.246 | 92.35 | 151 | 147.6 | 136.8
48 | 2023-04-01 | 400.246 | 92.35 | 151.1 | 145.7 | 136 |  | 48 | 2023-04-01 | 400.246 | 92.35 | 151.1 | 145.7 | 136
49 | 2023-05-01 | 402.5 | 92.35 | 149.4 | 144.4 | 134.7 |  | 49 | 2023-05-01 | 402.5 | 92.35 | 149.4 | 144.4 | 134.7
50 | 2023-06-01 | 406.686 | 92.35 | 148.9 | 141.7 | 135 |  | 50 | 2023-06-01 | 406.686 | 92.35 | 148.9 | 141.7 | 135
51 | 2023-07-01 | 410.228 | 92.35 | 152.1 | 139.5 | 135.6 |  | 51 | 2023-07-01 | 410.228 | 92.35 | 152.1 | 139.5 | 135.6
52 | 2023-08-01 | 409.262 | 92.35 | 152.5 | 140.8 | 136.2 |  | 52 | 2023-08-01 | 409.262 | 92.35 | 152.5 | 140.8 | 136.2
53 | 2023-09-01 | 402.5 | 92.35 | 151.8 | 143.8 | 134.9 |  | 53 | 2023-09-01 | 402.5 | 92.35 | 151.8 | 143.8 | 134.9
54 | 2023-10-01 | 412.482 | 92.35 | 152.5 | 143.1 | 136.7 |  | 54 | 2023-10-01 | 412.482 | 92.35 | 152.5 | 143.1 | 136.7
55 | 2023-11-01 | 409.906 | 92.35 | 153.1 | 143.2 | 135.3 |  | 55 | 2023-11-01 | 409.906 | 92.35 | 153.1 | 143.2 | 135.3
56 | 2023-12-01 | 409.262 | 92.35 | 151.8 | 139.7 | 135.9 |  | 56 | 2023-12-01 | 409.262 | 92.35 | 151.8 | 139.7 | 135.9
57 | 2024-01-01 | 410.872 | 92.35 | 151.2 | 138.3 | 135.5 |  | 57 | 2024-01-01 | 410.872 | 92.35 | 151.2 | 138.3 | 135.5
58 | 2024-02-01 | 417.312 | 92.35 | 151.2 | 138.3 | 134.1 |  | 58 | 2024-02-01 | 417.312 | 92.35 | 151.2 | 138.3 | 134.1
59 | 2024-03-01 | 412.482 | 91.315 | 151.4 | 138.9 | 132 |  | 59 | 2024-03-01 | 412.482 | 91.315 | 151.4 | 138.9 | 132
60 | 2024-04-01 | 411.516 | 90.28 | 152.9 | 142.3 | 131.1 |  | 60 | 2024-04-01 | 411.516 | 90.28 | 152.9 | 142.3 | 131.1
61 | 2024-05-01 | 416.024 | 90.28 | 153.5 | 144.5 | 129.3 |  | 61 | 2024-05-01 | 416.024 | 90.28 | 153.5 | 144.5 | 129.3
62 | 2024-06-01 | 416.668 | 90.28 | 154 | 143.6 | 126.8 |  | 62 | 2024-06-01 | 416.668 | 90.28 | 154 | 143.6 | 126.8
63 | 2024-07-01 | 421.176 | 90.28 | 155.3 | 139.7 | 124 |  | 63 | 2024-07-01 | 421.176 | 90.28 | 155.3 | 139.7 | 124
64 | 2024-08-01 | 422.142 | 90.28 | 154.4 | 138.6 | 122.6 |  | 64 | 2024-08-01 | 422.142 | 90.28 | 154.4 | 138.6 | 122.6
65 | 2024-09-01 | 422.142 | 90.28 | 154.7 | 138.9 | 125 |  | 65 | 2024-09-01 | 422.142 | 90.28 | 154.7 | 138.9 | 125
66 | 2024-10-01 | 424.074 | 90.28 | 156.7 | 140 | 124.6 |  | 66 | 2024-10-01 | 424.074 | 90.28 | 156.7 | 140 | 124.6
67 | 2024-11-01 | 426.65 | 90.28 | 156.4 | 140.2 | 125.3 |  | 67 | 2024-11-01 | 426.65 | 90.28 | 156.4 | 140.2 | 125.3
68 | 2024-12-01 | 427.616 | 90.31 | 155.7 | 139.5 | 127.9 |  | 68 | 2024-12-01 | 427.616 | 90.31 | 155.7 | 139.5 | 127.9
69 | 2025-01-01 | 431.158 | 90.34 | 155 | 138.5 | 128.2 |  | 69 | 2025-01-01 | 431.158 | 90.34 | 155 | 138.5 | 128.2
70 | 2025-02-01 | 431.48 | 90.34 | 154.9 | 138.7 | 128.9 |  | 70 | 2025-02-01 | 431.48 | 90.34 | 154.9 | 138.7 | 128.9
71 | 2025-03-01 | 431.158 | 90.34 | 154.8 | 140 | 129.3 |  | 71 | 2025-03-01 | 431.158 | 90.34 | 154.8 | 140 | 129.3
72 | 2025-04-01 | 431.48 | 90.34 | 154.2 | 140.8 | 127.6 |  | 72 | 2025-04-01 | 431.48 | 90.34 | 154.2 | 140.8 | 127.6
73 | 2025-05-01 | 435.666 | 90.34 | 153.7 | 138.7 | 131 |  | 73 | 2025-05-01 | 435.666 | 90.34 | 153.7 | 138.7 | 131
74 | 2025-06-01 | 435.988 | 90.34 | 153.7 | 137.2 | 131.3 |  | 74 | 2025-06-01 | 435.988 | 90.34 | 153.7 | 137.2 | 131.3
75 | 2025-07-01 | 441.784 | 90.34 | 154.4 | 135.4 | 131.4 |  | 75 | 2025-07-01 | 441.784 | 90.34 | 154.4 | 135.4 | 131.4
76 | 2025-08-01 | 444.682 | 90.34 | 155.2 | 135.8 | 131 |  | 76 | 2025-08-01 | 444.682 | 90.34 | 155.2 | 135.8 | 131
77 | 2025-09-01 | 444.682 | 90.34 | 155.2 | 135.8 | 131 |  | 77 | 2025-09-01 | 444.682 | 90.34 | 155.2 | 135.8 | 131